PROJECT PLAN

PaddleOCR Fine-Tuning Plan for Bangladesh NID

Phase-wise execution plan • PP-OCRv5 detection + unified Bangla-English recognition

Ultimate goal Adapt the existing PaddleOCR PP-OCRv5 detection + recognition pipeline to Bangladesh NID documents, with one unified Bangla + English recognition path, and produce a reproducible fine-tuning workflow that can later scale from a 2–4 NID smoke test to a real labelled dataset.

Scope focus: model fine-tuning only

Not a preprocessing or parser-logic improvement project.

Project Direction & Deliverables

The plan is intentionally narrow: improve model weights and training workflow, not surrounding software logic.

CURRENT STARTING POINT The reviewed NID service uses stock PP-OCRv5 server detection and server recognition checkpoints. The fine-tuning project keeps this PaddleOCR family and adapts both components to Bangladesh NID data.

PROJECT OVERRIDE Earlier material suggested treating Bengali as a separate OCR workstream. This task deliberately does not do that: the target is one PaddleOCR pipeline and one recognition path that handles Bangla + English together. Phase 01 verifies the exact supported training mechanics before implementation.

Ultimate Goals

•  Fine-tune PP-OCRv5_server_rec for Bangladesh NID text, including Bangla + English in one recognition vocabulary/training path.

•  Fine-tune PP-OCRv5_server_det for NID text-region layout, dense lines, clipping, merging and multi-line regions.

•  Build a reproducible train → evaluate → export → reload workflow, first proven on only 2–4 NIDs.

•  Define a defensible real-data target and a method for deciding when more NID data stops giving useful gains.

•  Deliver a clean repository that another engineer can run without committing real NID images.

Deliverables & Completion Map

Each deliverable has a specific completion gate; “started” does not mean “finished.”

| D1 — Fine-tuning documentation | Built throughout Phases 00–11. Complete at Phase 11 after the version-correct commands, dataset formats, configs, evaluation path and repo workflow have all been verified. |
| --- | --- |
| D2 — 2–4 NID fine-tuning scripts | Built in Phases 02–08. Complete at Phase 08 when the exported fine-tuned detector and recognizer both reload and run together inside PaddleOCR. |
| D3 — Data requirement recommendation | Prepared in Phase 10. Complete when the staged data targets and learning-curve decision method are documented. |
| D4 — Repository | Assembled continuously. Complete at Phase 11 when a clean checkout can reproduce the smoke-test workflow using a private external dataset path. |

DELIVERABLE TIMELINE Phase 08 finishes D2 • Phase 10 finishes D3 • Phase 11 finishes D1 + D4. At that point all requested deliverables are complete.

PHASE 00

Lock Scope & Success Criteria

Prevent the task from drifting into preprocessing, parser heuristics or a second OCR model.

WHY THIS PHASE EXISTS Prevent the task from drifting into preprocessing, parser heuristics or a second OCR model.

Tasks

□  Record exact in-scope targets: PP-OCRv5_server_det and PP-OCRv5_server_rec.

□  State that recognition must be unified Bangla + English, not split into separate OCR engines.

□  Define the 2–4 NID run as a process smoke test, not an accuracy claim.

□  Define model-level success metrics separately for detection and recognition.

□  Write explicit out-of-scope items: preprocessing upgrades, parser redesign and field-routing logic.

| Output | SCOPE.md + success criteria section in the main documentation. |
| --- | --- |
| Exit criterion | Everyone can explain what will and will not be changed before any training code is written. |
| Deliverable impact | D1 begins here; D4 gets its first project document. |

IMPORTANT Do not let “field extraction” silently turn into parser work. Fine-tuning may improve what text is seen/read, but mapping correct text into father_name/address JSON remains interpretation logic.

PHASE 01

Verify the Exact PaddleOCR Training Mechanics

Remove the main technical uncertainty before writing configs: how this installed PP-OCRv5 recognizer handles a custom Bangla + English vocabulary.

WHY THIS PHASE EXISTS Remove the main technical uncertainty before writing configs: how this installed PP-OCRv5 recognizer handles a custom Bangla + English vocabulary.

Tasks

□  Pin PaddleOCR / PaddlePaddle / PaddleX versions used for the experiment.

□  Locate the exact PP-OCRv5_server_rec and PP-OCRv5_server_det training configs and entrypoints for that version.

□  Verify how a custom recognition dictionary changes the recognizer head / checkpoint loading.

□  Verify Unicode handling for Bangla letters, vowel signs, virama and conjunct sequences.

□  Record exact train, eval and export commands that work in the pinned environment.

| Output | VERSION_NOTES.md + verified base configs. |
| --- | --- |
| Exit criterion | A tiny dummy training command can start with the intended custom character dictionary and pretrained weights. |
| Deliverable impact | D1 gains the version-correct procedure; D2/D4 are unblocked. |

IMPORTANT Do not copy commands from a different PaddleOCR major version without testing them in the pinned environment.

PHASE 02

Capture the Stock Baseline on 2–4 NIDs

Create the before-fine-tuning reference that proves later outputs came from a changed model rather than from memory or guesswork.

WHY THIS PHASE EXISTS Create the before-fine-tuning reference that proves later outputs came from a changed model rather than from memory or guesswork.

Tasks

□  Run stock PP-OCRv5_server_det + PP-OCRv5_server_rec on 2–4 representative NIDs.

□  Save detected polygons, recognized strings and confidence scores.

□  Render or save box-overlay images so missed, merged or clipped regions are visible.

□  Keep raw model output before any parser or regex layer.

□  Store results under a reproducible experiment folder.

| Output | baseline/ outputs: JSON + detection overlays + raw OCR text. |
| --- | --- |
| Exit criterion | The same 2–4 NIDs can later be run through the fine-tuned detector + recognizer for side-by-side inspection. |
| Deliverable impact | D2 gains its inference/baseline script; D4 gains experiment structure. |

PHASE 03

Design the Two Training Datasets

Prepare the correct annotation target for each model: geometry for detection and exact text for recognition.

WHY THIS PHASE EXISTS Prepare the correct annotation target for each model: geometry for detection and exact text for recognition.

Tasks

□  For detection: annotate whole NID images with text-line polygons/quadrilaterals.

□  For recognition: create single-line crops with exact ground-truth transcriptions.

□  Keep front and back NID text, including Bangla labels, names, parents’ names and addresses when present.

□  Decide a consistent policy for line breaks, punctuation, spaces and visually joined text.

□  Split by physical card, never by crop, so lines from the same NID do not leak across train/validation.

| Output | DATASET_FORMAT.md + small annotated sample dataset. |
| --- | --- |
| Exit criterion | Dataset loaders can read both detection annotations and recognition label files without path or encoding errors. |
| Deliverable impact | D1 dataset section advances; D2 gets training inputs; D4 gains dataset-preparation code. |

PHASE 04

Build the Unified Bangla + English Character Vocabulary

Make the recognizer capable of emitting every character that actually appears on Bangladesh NIDs.

WHY THIS PHASE EXISTS Make the recognizer capable of emitting every character that actually appears on Bangladesh NIDs.

Tasks

□  Scan all recognition ground-truth strings and collect required Unicode characters.

□  Include English letters, digits and only the punctuation actually seen on NIDs.

□  Include Bangla letters, vowel signs, anusvara/visarga/chandrabindu, virama and other observed code points.

□  Inspect conjunct examples to ensure the label encoding matches the recognizer’s token/dictionary mechanics.

□  Generate the dictionary automatically from labels and version the generated file.

| Output | scripts/build_charset.py + bangla_english_nid_dict.txt + charset notes. |
| --- | --- |
| Exit criterion | Every training label is representable by the dictionary and no “unknown character” cases remain. |
| Deliverable impact | D1 documents bilingual vocabulary; D2 gets a critical preprocessing-of-labels script; D4 gains reproducibility. |

IMPORTANT This is a recognition-model requirement, not image preprocessing. The dictionary must be generated from real ground truth rather than improvised by hand.

PHASE 05

Assemble the 2–4 NID Smoke-Test Dataset

Create the smallest possible dataset that can prove the whole fine-tuning pipeline works end to end.

WHY THIS PHASE EXISTS Create the smallest possible dataset that can prove the whole fine-tuning pipeline works end to end.

Tasks

□  Use the 2–4 NIDs to produce detection annotations and recognition crops.

□  Create a tiny train/validation split by card.

□  Run dataset validation checks for file paths, encoding, empty labels and missing characters.

□  Record sample counts: NID images, polygons and recognition lines.

□  Freeze this sample as a repeatable development fixture, using dummy/redacted examples in Git if real images cannot be stored.

| Output | smoke-test dataset package or private dataset layout + validation report. |
| --- | --- |
| Exit criterion | Both model trainers can load the tiny dataset and iterate over at least one training batch. |
| Deliverable impact | D2 training script is now testable; D4 gets a safe sample layout. |

IMPORTANT 2–4 NIDs are intentionally too small for meaningful accuracy conclusions. Passing this phase means “the pipeline works,” not “the model improved.”

PHASE 06

Fine-Tune Recognition First

Validate the easier half of the train → evaluate → export loop and prove the bilingual recognizer can update from pretrained weights.

WHY THIS PHASE EXISTS Validate the easier half of the train → evaluate → export loop and prove the bilingual recognizer can update from pretrained weights.

Tasks

□  Start from PP-OCRv5_server_rec pretrained weights; do not train from scratch.

□  Point the config to the Bangla + English dictionary and recognition crop labels.

□  Use a low learning rate and short smoke-test schedule.

□  Save checkpoints, training logs and validation CER/accuracy.

□  Export the trained checkpoint to an inference model directory and reload it independently.

| Output | train_rec script/config + exported bd_nid_rec_smoke model + logs. |
| --- | --- |
| Exit criterion | Exported recognizer loads successfully and produces text on held-out sample crops. |
| Deliverable impact | D2 recognition half complete; D1 has verified commands; D4 gains working recognition pipeline. |

IMPORTANT On this tiny set, overfitting is expected. We care about mechanical correctness, not the validation number.

PHASE 07

Fine-Tune Detection

Repeat the adaptation workflow for NID-specific text localization and line geometry.

WHY THIS PHASE EXISTS Repeat the adaptation workflow for NID-specific text localization and line geometry.

Tasks

□  Start from PP-OCRv5_server_det pretrained weights.

□  Point the detector config to NID images and polygon annotations.

□  Run a short smoke-test training schedule and save checkpoints/logs.

□  Evaluate using detection precision/recall/H-mean with IoU-based matching.

□  Export the trained detector and reload it independently.

| Output | train_det script/config + exported bd_nid_det_smoke model + logs. |
| --- | --- |
| Exit criterion | Exported detector loads successfully and returns polygons on sample NIDs. |
| Deliverable impact | D2 detection half complete; D1 and D4 gain the second training path. |

IMPORTANT The detector learns where text is; it does not learn that a line is “Father’s Name” or “Address.”

PHASE 08

Combine Exported Detector + Recognizer

Prove that both fine-tuned artifacts work together inside one PaddleOCR pipeline.

WHY THIS PHASE EXISTS Prove that both fine-tuned artifacts work together inside one PaddleOCR pipeline.

Tasks

□  Instantiate PaddleOCR using the custom detection model directory and custom recognition model directory.

□  Run the same 2–4 NIDs used for the baseline.

□  Save raw strings, scores and polygon overlays in the same output format as Phase 02.

□  Compare stock vs fine-tuned outputs manually for process verification.

□  Add a reload/rollback test so stock models can be restored easily.

| Output | test_finetuned_pipeline.py + combined outputs + model-path configuration example. |
| --- | --- |
| Exit criterion | A clean run loads both custom models together and returns OCR results without falling back to stock checkpoints. |
| Deliverable impact | D2 is finished here. D4 now contains an end-to-end executable workflow. |

PHASE 09

Evaluate at the Model Level

Measure the two neural components directly, without letting parser logic hide or create errors.

WHY THIS PHASE EXISTS Measure the two neural components directly, without letting parser logic hide or create errors.

Tasks

□  Recognition: report overall CER/accuracy plus Bangla-only, English-only and numeric subsets.

□  Detection: report precision, recall, H-mean/F1 and inspect missed/merged/split/clipped boxes.

□  Keep held-out data separate from all training/tuning decisions.

□  Save per-sample predictions so repeated glyph/spacing failures can be inspected.

□  Record stock and fine-tuned metrics using the same evaluation scripts.

| Output | evaluation scripts + EXPERIMENT_RESULTS.md template. |
| --- | --- |
| Exit criterion | The repo can produce repeatable detection and recognition metrics from a held-out set. |
| Deliverable impact | D1 gains the evaluation standard; D4 gains repeatable scoring. |

IMPORTANT Field-level parser F1 can be reported later, but it is not the primary metric for this model-fine-tuning task.

PHASE 10

Estimate the Real Data Requirement

Turn “how many NIDs are enough?” into a measurable data-scaling plan rather than a single magic number.

WHY THIS PHASE EXISTS Turn “how many NIDs are enough?” into a measurable data-scaling plan rather than a single magic number.

Tasks

□  Document 2–4 NIDs as smoke-test only and 50–100 as an exploratory learning-signal stage.

□  Use ~300–500 diverse NIDs and at least ~5,000 real recognition lines as an initial serious fine-tuning target, subject to coverage and learning curves.

□  Track Bangla character/conjunct coverage, NID-generation diversity and front/back field coverage — not only card count.

□  Train at increasing fractions of the dataset (for example 25/50/75/100%) and plot validation CER / detection H-mean.

□  Request more data while the held-out curve is still improving materially; stop adding similar data when gains flatten and analyze uncovered failure slices instead.

| Output | DATA_REQUIREMENT.md + staged sample-size table + learning-curve protocol. |
| --- | --- |
| Exit criterion | The team has a justified first collection target and a method for revising it with evidence. |
| Deliverable impact | D3 is finished here; D1 gains the scaling methodology. |

IMPORTANT The initial quantities are planning targets, not guarantees. Diversity and coverage can matter more than raw NID count.

PHASE 11

Finalize the Repository & Handoff

Package everything so another engineer can reproduce the workflow from a clean checkout with private data supplied separately.

WHY THIS PHASE EXISTS Package everything so another engineer can reproduce the workflow from a clean checkout with private data supplied separately.

Tasks

□  Organize docs, configs, scripts, sample/dummy data, model-output folders and experiment logs.

□  Add one-command or clearly ordered commands for prepare → train rec → train det → evaluate → export → combined test.

□  Keep real NID images and sensitive labels outside Git; use configurable dataset paths.

□  Pin dependencies and record hardware/environment assumptions.

□  Run the full smoke-test workflow from a clean checkout and fix every undocumented step.

| Output | Final repository + README + complete documentation set. |
| --- | --- |
| Exit criterion | Someone other than the original author can reproduce the smoke-test pipeline by following the repo docs. |
| Deliverable impact | D1 and D4 are finished here. Together with Phase 08 (D2) and Phase 10 (D3), all required deliverables are complete. |

IMPORTANT A repository is not “done” because scripts exist. It is done when the documented workflow is reproducible from a clean environment and private data is never required to be committed.

Recommended Repository Shape

Compact enough to understand quickly; explicit enough to reproduce the experiment.

bd-nid-paddleocr-finetune/
├── README.md
├── docs/
│   ├── SCOPE.md
│   ├── FINE_TUNING_PLAN.md
│   ├── DATASET_FORMAT.md
│   ├── BANGLA_ENGLISH_CHARSET.md
│   ├── DATA_REQUIREMENT.md
│   └── EXPERIMENT_RESULTS.md
├── configs/
│   ├── nid_det.yml
│   └── nid_rec.yml
├── scripts/
│   ├── prepare_detection_data.py
│   ├── prepare_recognition_data.py
│   ├── build_charset.py
│   ├── train_rec.sh
│   ├── train_det.sh
│   ├── eval_rec.sh
│   ├── eval_det.sh
│   ├── export_models.sh
│   └── test_finetuned_pipeline.py
├── dataset_sample/        # dummy/redacted only
├── models/                # generated, usually gitignored
└── requirements.txt

PRIVACY RULE Real Bangladesh NID images and real identity labels stay in access-controlled storage outside Git. The repository contains only code, configuration, documentation, and safe sample/dummy data.